## Wx
PROJECT REPORT
Group | Group 4
Week | 19/9/2021-25/9/2021
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Coding database | Pending
2 | Screen detailed analysis | Completed
3 | SRS file | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.) | Link
1 | SRS | All | Via discord
2 | Trainning Using Trello | Dương Trung Huy | Via Google Meet | https://drive.google.com/file/d/1ZBBJj6CiTXYjseSJHklvLCjZwlVND_nx/view?usp=sharing
3 | Analyze Database_demo1 | All | Via discord
4 | Created Database Diagram demo 1 | Nguyễn Trần Duy Vũ, Phan Nguyễn Đức Hiếu | Using Hieu diagram as the last version
5 | Trainning Using Git
6 | Completed Product-Backlog | Dương Trung Huy | Via Trello | https://trello.com/b/MhEebpyc/swp391
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Training tech | 15/8/2021
2 | Complete Backlog file | 17/8/2021
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C20: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue