## Wx
PROJECT REPORT
Group | Group 4
Week | 26/9/2021-25/9/2021
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Software Design | In Progress | Will be completed by iterations
2
3
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Home page | Luong Viet Thang | Done
2 | Subject List | Phan Nguyen Duc Hieu | Done
3 | Blog, Blog List | Vu Nguyen Tran Duy | Done
4 | login, register, forgot password | Nguyen Nam Phuong | Done
5 | admin page | Duong Trung Huy | Dash Broad Done
6 | user profile | Nguyen Nam Phuong | Done
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Common Feature | 2021-09-10 | Nguyễn Nam Phương
2 | Public Feature/Blog List | 9/10/2021 | Nguyễn Trần Duy Vũ
3 | Public Feature/Blog Detail
4 | Public Feature/Home |  | Lương Việt Thắng
5 | Public Feature/ Subject Detail | 13/10/2021 | Phan Nguyễn Đức Hiếu
6 | Public Feature/ Subject Register
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C20: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue