## Wx
PROJECT REPORT
Group | Group 4
Week | 26/9/2021-25/9/2021
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Software Design | In Progress | Will be completed by iterations
2
3
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Common Feature | Nguyen Nam Phuong | Done
2 | Blog List, Blog Detail | Nguyen Trang Duy Vu | Done
3 | Show product on Home Page | Luong Viet Thang | Done
4 | Subject List, Detail | Phan Nguyen Duc Hieu | Done
5 | Admin page | Duong Trung Huy | Dash Broad Done
6 | user profile | Nguyen Nam Phuong | in Progress
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Customer Feature | 2021-12-10 | Nguyễn Nam Phương, Lương Việt Thắng
2 | Learning Feature | 15/10/2021 | Nguyễn Trần Duy Vũ, Dương Trung Huy
3
4
5 |  | 20/10/2021 | Phan Nguyễn Đức Hiếu
6 | Course Content Feature
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C20: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue