## Functions
THE APPLICATION DEVELOPMENT PROJECT TOPIC (SWP391)
QUIZ PRACTICING SYSTEM ProductBacklog
Project: Online Shop |  | Total LOC: | 4680
# | Function/Screen | Feature | LOC | Level* | Function/Screen Details | Iteration | Deadline | In Charge | Support | Issues | Note | Completed Time | Status | In Time
1 | User Login | Common | 60 | Simple | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also options for user to register new information or reset the password for the case s/he forget it | Iteration 1 |  | Nguyễn Nam Phương |  |  |  | 2/10-9/10/2021 | Done | 2 Week
2 | User Register | Common | 60 | Simple | This is a pop-up screen which allows the user to register himself/herself to the system by inputing following information: full name, gender, email, mobile; User then need to verify by clicking the link sent via email to him/her before being able to access the system | Iteration 1 |  | Nguyễn Nam Phương |  |  |  |  | Done
3 | Reset Password | Common | 120 | Medium | The user to input his/her email to receive the reset password link. This link is sent to the user's email for his/her password resetting. - On clicking the link, the user is redirected to the password resetting page in which s/he input new password (twice) for the system access - Note that the link is only available for a specific time duration as configured in the system config file. | Iteration 1 |  | Nguyễn Nam Phương |  |  |  |  | Done
4 | User Authorization | Common | 240 | Complex | Implementation of authorization mechanism in the system, including the specify the role of logged-in user, his/her authorized page links (building the displayed menu items (in the front end) and preventing unauthorized access via enter the links directly) | Iteration 1 |  | Nguyễn Nam Phương |  |  |  |  | Done
5 | User Profile | Common | 60 | Simple | This is a pop-up screen which allows the user to edit his/her profile information, including the registered ones & the avatar image. Please note that s/he is not allowed to change the email | Iteration 1 |  | Nguyễn Nam Phương |  |  |  |  | Done
6 | Change Password | Common | 60 | Simple | This is a pop-up screen which allows the user to change his/her password by inputting his current password as well as new password (twice) | Iteration 1 |  | Nguyễn Nam Phương |  |  |  |  | Done
7 | Home | Public | 120 | Medium | Show sliders, hot posts, featured subjects + the sider with the latest posts, static contacts/links - Shown slider information includes its image and title; the user is redirected to the slider's backlink on his/her clicking - Shown post information includes its thumbnail, title, post date; the user is redirected to the post's details on his/her clicking - Shown subject information includes its thumbnail, title, tag line; the user is redirected to the subjectt's details on his/her clicking | Iteration 1 |  | Lương Việt Thắng |  |  |  |  | Done
8 | Blogs List | Public | 60 | Simple | Show the posts paginatedly (sorted by updated date) + the sider with the post search box, posts categories, latest posts, static contacts/links; Shown post information includes its thumbnail, title, category, brief-info; the user is redirected to the post's details on his/her clicking | Iteration 1 |  | Nguyễn Trần Duy Vũ |  |  |  | 2/10-9/10/2021 | Done
9 | Blog Details | Public | 60 | Simple | Show post details (including title, author, updated date, category, and post details) + the sider with the post search box, posts categories, latest posts, static contacts/links | Iteration 1 |  | Nguyễn Trần Duy Vũ |  |  |  |  | Done
10 | Subjects List | Public | 240 | Complex | Show the subjects paginatedly (sorted by updated date, paginated) + the sider with the subject search box, subject categories, featured subjects, and static contacts/links; - Shown subject information includes its thumbnail, title, tag line, lowest price package option (list price, sale price); - The user is redirected to the subject's details on his/her clicking on the subject - The user can choose to register to the subject by clicking the Register button | Iteration 1 |  | Phan Nguyễn Đức Hiếu |  |  |  | 2/10-13/10/2021 | Done
11 | Subject Details | Public | 120 | Medium | Show subject details (including title, tag line, brief info, lowest price package option (original price, sale price), product description, and a Register button) + the sider with the subject search box, subject categories, featured subjects, static contacts/links | Iteration 1 |  | Phan Nguyễn Đức Hiếu |  |  |  |  | Done
12 | Subject Register | Public | 120 | Medium | This is a pop-up screen which allow the user to register for access a subject. On this screen, the user needs to choose appropriate subject price package & input his/her information (full name, email, mobile, gender); A logged in user doesn't have to input those contact information | Iteration 1 |  | Phan Nguyễn Đức Hiếu |  |  |  |  | Done
13 | My Registrations | Customer | 60 | Simple | Show the list of user's registrations + the sider with the subject search box, subject categories, static contacts/links - Each registration includes below information: id, subject, registration time, package, total cost, status, valid from, valid to; - If the registration is still in the submitted status, the users can choose to cancel it or comming back to the Subject Register pop-up to edit it) | Iteration 2 |  | Nguyễn Nam Phương |  |  |  | 2021-12-10 | Done | 3 Week
14 | Practices List | Customer | 120 | Medium | This page allows the user to view the list of quiz practices that s/he has taken | Iteration 2 |  | Lương Việt Thắng | Nguyễn Nam Phương |  |  | 2021-12-10 | Done
15 | Practice Details | Customer | 60 | Simple | This page allows the user to input new practice information for practicing or to view his/her existing one | Iteration 2 |  | Lương Việt Thắng |  |  |  |  | Done
16 | Simulation Exams | Customer | 120 | Medium | This page allows the user to view the existing exams of the subject that s/he has the access. • List columns: id, subject, simulation exam, level, #question, duration, and pass rate • The user can filter the list by the subject + search list items by the exam name From the list, the user can choose to take the exam to see the exam details, and then to go to Quiz Handle page to practice that relevant simulation exam. | Iteration 2 |  | Lương Việt Thắng |  |  | Complete Exam CRUD later |  | Done
17 | Quiz Handle | Learning | 240 | Complex | This screen allows the user to browse and answer the quiz questions | Iteration 2 |  | Dương Trung Huy | Nguyễn Trần Duy Vũ |  |  | 15/10/2021 | Done
18 | Quiz Review | Learning | 240 | Complex | This screen allows the user to review the details of the quiz that s/he has just taken | Iteration 2 |  | Dương Trung Huy | Nguyễn Trần Duy Vũ |  |  |  | Done
19 | Dashboard | Marketing | 240 | Complex | Show statistics of new subjects (new, all), new registrations (success, cancelled, submitted), revenues (total, by subject categories), customers (newly registered, newly bought), and the trend of order counts (success, all) by day for the last 7 days (the start date & end date can be adjustable) | Iteration 2 |  | Dương Trung Huy |  |  |  |  | Done
20 | Post Details | Marketing | 120 | Medium | Show detailed post information (thumbnail, category, title, brief information, description, flag to turn the featurning on/off, status), from that allow the user to input, view or edit them | Iteration 2 |  | Nguyễn Trần Duy Vũ |  |  |  | 13/10/2021 | Done
21 | Sliders List | Marketing | 60 | Simple | Show the paginated list of sliders (including sliders' id, title, image, backlink, status) - The user can filter the sliders by the status + search by title or backlink - For each slider, the user can choose to hide, show, edit it | Iteration 2 |  | Lương Việt Thắng |  |  |  |  | Done
22 | Slider Details | Marketing | 60 | Simple | Show detailed slider information (image, title, backlink, status, notes) | Iteration 2 |  | Lương Việt Thắng |  |  |  |  | Done
23 | Subjects List | Course Content | 120 | Medium | Show the list of course paginatedly. The shown information for each subject include the id, name, category, number of lessons, owner, and status The user can: - Filter the list by course category & status - Search the course by the name - Choose to add new course (redirect the user to the New Subject page for that) - Edit course information (linked to the Subject Details for that) | Iteration 2 |  | Phan Nguyễn Đức Hiếu |  |  |  | 20/10/2021 | Done
24 | New Subject | Course Content | 120 | Medium | The screen is shown with below information for the user to input new course information: name, thumbnail image, category, featured flag, owner, status, and description | Iteration 2 |  | Phan Nguyễn Đức Hiếu |  |  |  |  | Done
25 | Subject Details | Course Content | 240 | Complex | This page allows the admin and the assigned expert to access and prepare the subject information, including the course general information, the dimension, and price package. Only the admin can change the status to Published or Unpublished + add/edit the price packages | Iteration 2 |  | Phan Nguyễn Đức Hiếu |  |  |  |  | Done
26 | Subject Dimension | Course Content | 60 | Simple | This page allow the admin/expert to input or edit subject dimension information, including the following detailed information: type, name, description | Iteration 2 |  | Phan Nguyễn Đức Hiếu |  |  |  |  | Done
27 | Price Package | Course Content | 60 | Simple | This page allows the admin to input or edit subject dimension information, including the following detailed information: name, access duration (in months), status (read-only), list price, sale price, description. The expert can only view the information. | Iteration 2 |  | Phan Nguyễn Đức Hiếu |  |  |  |  | Done
28 | Subject Lessons | Course Content | 120 | Medium | This page shows the list of lessons for a selected package. On this page, the admin/expert is allowed to activate/deactivate, or call the Lesson Details for adding new or editing existing lesson | Iteration 2 |  | Phan Nguyễn Đức Hiếu |  |  |  |  | Done
29 | Lesson Details | Course Content | 120 | Medium | This page allows the admin/expert to input/edit the lesson information | Iteration 2 |  | Phan Nguyễn Đức Hiếu |  |  |  |  | Done
30 | Questions List | Test Content | 120 | Medium | The existing questions list for a specific subject/course are shown here (paginatedly). On this screen, the admin/expert is allowed to filter the questions by the subject, lesson, dimension(s), level, status + search the questions by content Below information are shown for each quesiton in the list: id, content, subject /dimension /lesson, level, status + options to show, hide, edit it; The page also allows the user to import the question (redirect him/her to the Questions Import pop-up screen. | Iteration 3 |  | Lương Việt Thắng |  |  |  |  | In Progress | 2 Week
31 | Question Details | Test Content | 240 | Complex | This page allows the admin/expert to input or edit questions information, including following information: subject, dimension(s), lesson, status, content, media (image, audio, video – with preview option), answer options (with the key marked + ability to add, edit, delete), and explanation | Iteration 3 |  | Lương Việt Thắng |  |  |  |  | In Progress
32 | Question Import | Test Content | 120 | Medium | This is a pop-up screen which allows user to choose import file and then import the questions in the file into the questions bank. The screen also provides the option for the user to download the sample import template. | Iteration 3 | [6 empty] | In Progress
33 | Quizzes List | Test Content | 120 | Medium | The existing quizzes are showned in this page paginatedly: - The user can filter the list by subject, quiz types + search quizzes by the name - Each quiz includes following information: id, name, subject, level, # question, duration, pass rate, and the quiz type. From this page, the user has the options to call to the Quiz Details page for adding new or editing existing quiz + delete the quiz. Please note that the quiz can be editted only when there is not any test taken yet. | Iteration 3 |  | Lương Việt Thắng |  |  |  |  | In Progress
34 | Quiz Details | Test Content | 120 | Medium | This page allows the user to input or edit quiz information | Iteration 3 |  | Lương Việt Thắng |  |  |  |  | In Progress
35 | Registrations List | Sale | 120 | Medium | Show the list of users' registrations - Each registration includes below information: id, email, registration time, subject, package, total cost, status, valid from, valid to, last updated by; - The user can filter the list by subject (searchable), registration time (from, to), status + can search by the email - The list can be sorted by id, email, registration time, subject, package, total cost, status, valid from, valid to - From the list, the user can choose to add new or edit an existing registration via the Registration Details screen as below | Iteration 3 | [6 empty] | In Progress
36 | Registration Details | Sale | 120 | Medium | Show detailed registration information (subject, package with list price/sale price, full name, gender, email, mobile), registration time, sale, status, valid from, valid to, notes) from that for the user to add new or change the status of a registration with relevant notes (if a registration is created by the user, then s/he can edit other registration information). On changing a registration status to Paid, if the user with relevant registered email does not exist, the system would create one and send back to the user the login information (link, email, pass) along with the other notification notes | Iteration 3 | [6 empty] | In Progress
37 | Users List | Admin | 60 | Simple | Show the paginated list of registered users (include users' id, full name, gender, email, mobile, role, status): - The admin can filter the users by gender, role, status - Allow the admin to seach users by full name, email, mobile - The list is sortable by id, fullname, gender, email, mobile, role, status - From each user, the admin can choose to view or edit it - The page also have the button/link that allows the admin to add new user | Iteration 3 |  | Dương Trung Huy |  |  |  |  | In Progress
38 | User Details | Admin | 60 | Simple | Show detailed user information (avatar, full name, gender, email, mobile, role, address, status), from that allow the user to add new, view or edit user information - After adding, new generated login password would be email to the new user - The admin can only edit/update the role and status of the user | Iteration 3 |  | Dương Trung Huy |  |  |  |  | In Progress
39 | Settings List | Admin | 60 | Simple | Show the paginated list of settings (include settings' id, type, value, order, status): - The admin can filter the setting by type, status - Allow the admin to seach settings by value - The list is sortable by id, type, value, order, status - From each setting, the admin can choose to view, activate/deactivate, or edit it - The page also have the button/link that allows the admin to add new setting | Iteration 3 |  | Dương Trung Huy |  |  |  |  | In Progress
40 | Setting Details | Admin | 60 | Simple | Show detailed user information (type, value, order, description, status), from that allow the user to add new, view or edit setting information | Iteration 3 |  | Dương Trung Huy |  |  |  |  | In Progress

## Screen Build
Screens | in charge | level | deadline | Status | Note | Issues
Home page | Luong Viet Thang | Complex | 2021-02-10 | Done
Subject List/subject detail | Phan Nguyen Duc hieu | Medium | 30/9/2021
blog, blog list | Vu Nguyen Tran Duy | Medium | 30/9/2021 | Done
login, register, forgot password | Nguyen Nam Phuong | Easy | 28/9/2021 | Done
admin page | Duong Trung Huy | Complex | In Future | In Progess
user profile | Nguyen Nam Phuong | Medium | 2021-02-10 | Done
Practice list + detail | Luương Việt Thắng | Medium | 2021-07-10 | Done

## Training Plan
Week | Iteration | Date | Time | Content | In charge (FullName) | Link Drive | Status | Quantity | Note
2 | 1 | 13-9-2021 | 20h-22h | Training Trello and Analyze Database | Duong Trung Huy and Team | https://drive.google.com/file/d/1ZBBJj6CiTXYjseSJHklvLCjZwlVND_nx/view | Done | 100%
|  | 16-9-2021 | 20h30-22h30 | Training GitHub basic using | Duong Trung Huy | https://drive.google.com/file/d/12KZ8naSeBOe09JDiLSu0SWz-tLvBhyzw/view?usp=sharing | Done | 100%
|  | 17-9-2021 | 20h30-22h30 | Training Github basic using confirmation | Phan Đức Hiếu and Dương Trung Huy | https://drive.google.com/file/d/12KZ8naSeBOe09JDiLSu0SWz-tLvBhyzw/view?usp=sharing | Done | 100% | Đảm bảo mọi thành viên đều có thể sử dụng git
|  | 18-9-2021 | 14h30-16h30 | Training Jquery | Duong Trung Huy | https://drive.google.com/file/d/1aRR9OxXoDYxQg8Nlg1CfLEucLjmBAZ0L/view?usp=sharing | Done | 80% | Thiếu Vũ
|  | 18-9-2021 | 20h-22h30 | Training boostrap | Phan Đức Hiếu | https://drive.google.com/file/d/1aRR9OxXoDYxQg8Nlg1CfLEucLjmBAZ0L/view | Done | 100%